## Test Plan & Summary
Project Name | QA Engineer Assessment Submission
Tested Web Application | SauceDemo
Tested API | JSONPlaceholder
Core User Story | As a user, I want to add a product to my cart and complete the checkout process so that I can successfully purchase the item.
Tester/Author | John Michael Lorena
Submission Date | 2025-12-03
Area of Evaluation | Total Tests Run | Passed | Failed | Key Findings
Web UI: Login & Access | 4 | 3 | 1 | Functional login logic is stable, and specialized error handling (locked-out user) works as designed. A critical UI defect was identified where the invalid login error message overlaps the login form, negatively impacting UX.
Web UI: Add to Cart | 5 | 4 | 1 | Core Add/Remove functionality is stable for the standard user. Critical functional failures were exposed when testing with the problem_user, resulting in multiple defects related to data integrity (missing items, incorrect prices, and non-functional remove buttons).
Web UI: Checkout Process | 4 | 2 | 2 | Form validation is functional (required fields). However, two major flow/logic defects were found: Critical flaw allows checkout with an empty cart (TC-O-002), and an inconsistent flow defect on the Checkout: Overview page incorrectly redirects the "Cancel" button to the Inventory page (TC-O-004).
API: Functional Testing | 9 | 8 | 1 | All required endpoints were covered with positive and negative/edge cases. Data retrieval (GET/PUT) is robust, but the POST endpoint failed to enforce data validation (API-P002), highlighting a critical data integrity risk.
Deliverable | Status | Location in Repository | Notes
Manual Test Cases | Complete | This Workbook (Sheets 2-4) | Covers positive, negative, and edge cases for all features.
API Test Documentation | Complete | This Workbook (Sheet 5: API Testing) | Includes request/response details and specific assertions.
Automation Script (Playwright) | Complete | web-app-testing/ | Used Page Object Model for maintainability.
Bug Reports | Complete | documentation/bug_reports.md | Contains 1 documented issue/risk for the JSONPlaceholder POST endpoint.

## Login & Access Tests
ID | Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Screenshot/Evidence
TC-L-001 | Verify successful login with the standard user. | User is on the login page. | 1. Enter Username. 2. Enter Password. 3. Click Login. | Username:standard_user Password:secret_sauce | User is successfully redirected to the Products page (/inventory.html). | User was successfully redirected to https://www.saucedemo.com/inventory.html | PASS
TC-L-002 | Verify login failure for a locked-out user (Negative). | User is on the login page. | 1. Enter Username. 2. Enter Password. 3. Click Login. | Username:locked_out_user Password:secret_sauce | A specific error message is displayed: "Epic sadface: Sorry, this user has been locked out." | The exact expected error message was displayed below the login form. | PASS
TC-L-003 | Verify behavior for a "Problem User" (Edge). | User is on the login page. | 1. Enter Username. 2. Enter Password. 3. Click Login. | Username:problem_user Password:secret_sauce | User logs in, but product images are broken (as expected behavior for this test user). | User successfully logged in and was redirected to the Products page. All product images appeared incorrect. | PASS
TC-L-004 | Verify handling of invalid credentials (Negative). | User is on the login page. | 1. Enter incorrect username/password. 2. Click Login. | Username:invalid_user Password:wrong_password | A generic login error message is displayed: "Epic sadface: Username and password do not match..." | The expected error message was displayed. However, the warning text overlapped with the login form, obscuring part of the message. | FAIL

## Add to Cart Tests
ID | Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Screenshot/Evidence
TC-C-001 | Verify adding a single item to the cart (Positive). | Logged in as standard_user. | 1. Click "Add to Cart" for one product. | standard_user | 1. Button text changes to "Remove". 2. Cart badge displays "1". | Both conditions met: Button text changed to "Remove," and the cart badge displayed "1." | PASS
TC-C-002 | Verify adding all items to the cart (Boundary). | Logged in as standard_user. | 1. Click "Add to Cart" for all 6 products. 2. View the Cart page. | standard_user | All 6 items are added, and the cart badge displays "6". | All 6 items were added to the cart, and the cart badge correctly displayed "6." | PASS
TC-C-003 | Verify item removal from the Products page (Negative). | Logged in as standard_user., one item is in the cart. | 1. Click the "Remove" button on the Products page. | standard_user | The item is removed, and the cart badge decreases or disappears. | Item was successfully removed from the cart and the badge decreased to the correct number. | PASS
TC-C-004 | EDGE: Test Add to Cart with problem_user | Logged in as problem_user. | 1. Observe broken images. 2. Click "Add to Cart" for an item. | problem_user | PASS: Although the images are broken, the Add to Cart functionality must still work. The cart badge should still update to "1". | Multiple Defects Observed: 1. The Add to Cart button failed to add specific items. 2. Items that were added could not be removed. 3. Items displayed the wrong price on the Products page and/or Cart page. 4. One item appeared to be missing/not found upon checking the cart. | FAIL
TC-C-005 | EDGE: Test speed/timing with performance_glitch_user | Logged in as performance_glitch_user | 1. Click "Add to Cart" and immediately navigate to another page. | performance_glitch_user | PASS: Despite the slow page load, the click event should successfully register, and the item should be in the cart upon navigation. | Item was successfully added to the cart after the slow page load completed. Verified item was present on the Cart page. | PASS

## Checkout Process Tests
ID | Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Screenshot/Evidence
TC-O-001 | Happy Path Checkout (Positive - Core AC). | Logged in as standard_user , at least one item in the cart. | 1. Go to Cart, click Checkout. 2. Enter valid checkout info (Step 1). 3. Click Continue (Step 2). 4. Click Finish (Step 3). | First: John, Last: Doe, Postal: 12345 | The final page, "Checkout: Complete!" is displayed with the "Thank You for Your Order!" message. | The purchase completed successfully. The user was redirected to the "Checkout: Complete!" page, and the confirmation message was displayed. | PASS
TC-O-002 | Attempt checkout with an empty cart (Negative). | Logged in as standard_user , cart is empty. | 1. Manually navigate to the Cart page URL. 2. Click the Checkout button (if visible). | N/A | The system prevents navigation to the checkout step, or the checkout button is disabled/missing. | User was able to bypass the cart check and proceed through the entire checkout flow (Information, Overview, and Finish) even though the cart was completely empty. | FAIL
TC-O-003 | Missing required fields in Checkout Step 1 (Negative). | Logged in, one item in cart, on Checkout Step 1. | 1. Leave the First Name field empty. 2. Enter valid Last Name and Zip Code. 3. Click Continue. | First: (empty), Last: Doe, Postal: 12345 | An error message is displayed below the form: "Error: First Name is required". | The system correctly prevented form submission and displayed the error message "Error: First Name is required." | PASS
TC-O-004 | Verify "Cancel" button on Checkout Step 1 (Edge). | Logged in, on Checkout Step 1. | 1. Click the Cancel button. | N/A | User is redirected back to the Cart page (/cart.html) | Defect Observed: The Cancel button on Checkout: Overview page (Step 2) incorrectly redirects the user to the Products/Inventory page (/inventory.html) instead of the Cart page. | FAIL

## API Test Documentation
Test ID | Endpoint | Method | Case Type | Test Description | Request URL | Request Body | Expected Status | Key Assertions | Actual Status | Short Analysis / Result
API-G001 | /users | GET | Positive | Retrieve all users. | https://jsonplaceholder.typicode.com/users | N/A | 200 OK | 1. Status code is 200. 2. Response body is an Array. 3. Array length is 10. | 200 | PASS. Confirmed array structure and expected collection size.
API-G002 | /users | GET | Edge | Use an invalid/ignored query parameter (e.g., ?limit=1). | https://jsonplaceholder.typicode.com/users | N/A | 200 OK | 1. Status code is 200. 2. Response body size is still 10 (confirming parameter was ignored). | 200 | PASS. API handled the unsupported parameter gracefully.
API-G003 | /users/1 | GET | Positive | Retrieve user with ID 1. | https://jsonplaceholder.typicode.com/users/1 | N/A | 200 OK | 1. Status code is 200. 2. Response body is an Object. 3. id property equals 1. 4. Contains email property. | 200 | PASS. Verified structure and correct data retrieval for a single resource.
API-G004 | /users/id | GET | Negative | Retrieve a user with a non-existent ID (e.g., /users/999). | https://jsonplaceholder.typicode.com/users/999 | N/A | 404 Not Found | 1. Status code is 404. 2. Response body is empty JSON object ({}). | 404 | PASS. Confirmed API correctly returns 404 for missing resources.
API-P001 | /posts | POST | Positive | Create a new post with all mandatory fields. | https://jsonplaceholder.typicode.com/posts | {"title": "Test Post", "body": "lorem", "userId": 1} | 201 Created | 1. Status code is 201. 2. Response body contains a new id. 3. Returned title matches sent title (Data Persistence). | 201 | PASS. Resource successfully created.
API-P002 | /posts | POST | Negative | Attempt to create a post with the title field missing. | https://jsonplaceholder.typicode.com/posts | {"body": "lorem", "userId": 1} | 400 Bad Request (Standard expectation) | 1. Status code is not 201. 2. If 201 is returned, assert that the returned title is empty/null. | 201 | FAIL. API incorrectly returned 201 Created. This is documented as API Risk 001 in bug_reports.md (Data Integrity Risk).
API-U001 | /posts/1 | PUT | Positive | Update the title and body of an existing post. | https://jsonplaceholder.typicode.com/posts/1 | {"id": 1, "title": "UPDATED Title", "body": "New content", "userId": 1} | 200 OK | 1. Status code is 200. 2. Returned title matches sent updated title. 3. Returned id is still 1. | 200 | PASS. Resource successfully updated and verified.
API-U002 | /posts/id | PUT | Edge | Attempt to update a non-existent post (e.g., /posts/99999). | https://jsonplaceholder.typicode.com/posts/1 | {"id": 99999, "title": "Test"} | 404 Not Found | 1. Status code is 404. 2. Response body is empty or {}. | 404 | PASS. Confirmed API correctly handles attempts to modify a non-existent resource.